## Sheet1
Id | User story | Story points | Status
1 | User login to the system | 3 | Inprogress
2 | User forgot the password | 5 | Open
3 | Create a user from the app | 7 | Open
4 | Admin add/update/remove subject to the app | 7 | Open
5 | Admin add/update/remove subject to the app | 7 | Open
6 | Admin enable/disable the user | 7 | Open
7 | Admin reset the user account | 7 | Open
8 | Admin set report columns | 7 | Open
9 | Admin edit user privilages | 7 | Open
10 | Student view profile/edit profile | 7 | Open
11 | Student view subject details | 5 | Open
12 | Student view assignments | 5 | Open
13 | Student upload/edit documents to assignment | 7 | Open
14 | Student view results | 7 | Open
15 | Student view notes of the subject | 7 | Open
16 | Student download notes of the subjects | 7 | Open
17 | Student view timetable | 7 | Open
18 | Admin prepare the timetable | 7 | Open
19 | Admin prepare the sitenews | 7 | Open
20 | Student view sitenews | 7 | Open
21 | Tutor view/edit profile | 7 | Open
22 | Tutor view time table | 7 | Open
23 | Tutor view class details | 7 | Open
24 | Tutor view/get report of subject results | 7 | Open
25 | Tutor view/get student subject results. | 7 | Open
26 | Admin upload student results to the app | 13 | Open